Phases and Tasks

Phase 1: Planning & Requirement Gathering (1 – 7 August 2025)

- Formally define project scope and objectives.

- Target three groups: lecturers, programme managers, and coordinators.

- Document roles for claims submission, review, and approval processes.

- Core functionalities including user login, claims creation, approval, and dashboard access must be documented.

Phase 2: System & Database Design (8 – 14 August 2025)

- Create wireframes for Login, Registration, Dashboard, and Claims pages.

- Develop a system flow diagram illustrating the claim lifecycle from submission to approval/rejection.

- Design an InMemoryStore database structure with Users and Claims.

Phase 3: Development (15 – 27 August 2025)

Frontend Development (15 – 20 August 2025):

- Construct the user interface using Razor Views along with HTML and CSS.

- Ensure Login and Registration forms allow role selection.

- Develop two dashboard types: Lecturer’s “My Claims” and Manager/Coordinator’s “Manage Claims."

- Apply consistent header/footer and inline CSS across all pages.

Backend Development (21 – 24 August 2025):

- Implement role-based access and session authentication.

- Configure InMemoryStore for managing claims and users.

- Enable claims submission for instructors.

- Establish approval workflows for managers and coordinators.

Integration (25 – 27 August 2025):

  - Connect controllers and models with Razor Views.

  - Ensure claims are updated, stored, and displayed correctly.

  - Verify form entries and enforce file limitations.

Phase 4: Quality Assurance (28 August – 2 September 2025)

- Conduct integration testing for claims, role-based access, and login functionalities.

- Perform usability testing for all user types.

- Assess session management capabilities.

- Test responsiveness on mobile devices and across browsers.

- Debug issues and enhance the user interface.

Phase 5: Deployment & Documentation (3 – 5 September 2025)

## Deploy the prototype on a server (hosted/local).

## Develop user and technical documentation, encompassing usage and role authorization details.

## Present the system to stakeholders.

## 3. Dependencies

## Requirement completion is essential before design; development initiation waits on design finalization.

## 4. Timeline with Dates

| Dates | Tasks |
| --- | --- |
| 1 – 7 Aug 2025 | Requirement gathering, scope, role definitions, use cases, documentation |
| 8 – 14 Aug 2025 | System design, wireframes, data schema, validation rules |
| 15 – 20 Aug 2025 | Frontend development (UI, forms, dashboards, styling) |
| 21 – 24 Aug 2025 | Backend development (authentication, InMemoryStore, claim workflows) |
| 25 – 27 Aug 2025 | Integration (frontend + backend, validation, workflows) |
| 28 Aug – 2 Sep 2025 | Quality assurance ( debugging, cross-browser checks, refinements) |
| 3 – 5 Sep 2025 | Deployment, user guide, technical documentation, presentation |

5. Risk Management

Risks include circumvention of roles, data loss upon InMemoryStore restart, and usability issues. Mitigations are defined to address these.

6. Milestones

7 Aug 2025: Finalized requirements. 
14 Aug 2025: Completed design. 
27 Aug 2025: Developed functional prototype. 
2 Sep 2025: Completed testing and refinements. 
5 Sep 2025: Submitted final project.